## Slide 1: Leadership Institute IV- Call to Action Project Presentation
Migration from Ariel to ILLiad and Odyssey

## Slide 2: DSU Presenters
William C. Jason Library
Dover, Delaware
Dr. Rebecca E. Batson
Dean of University
Libraries
Mrs. Beverly D. Charlot
Coordinator of Technical
Services

## Slide 3: Abstract
Resource Sharing and Research: Getting What You Need by Effectively Improving Interlibrary Loan Processes and Procedures using the Interlibrary Loan Internet Accessible Database (ILLiad) software
William C. Jason Library
Dover, Delaware

## Slide 4: Abstract - Continued
Interlibrary Loan (ILL) requests have increased tremendously at Delaware State University (DSU) in the last 3 years. Library staff documented the increase and tracked the delay in time from submitting and receiving a request. ILL staff also recognized that many articles were already owned by DSU in various full text databases.
To effectively serve the university research community ILLiad Resource Sharing Management software 8.2 was purchased to improve ILL service.

## Slide 5: Abstract- Continued
ILLiad management software is seamless and allows faculty and students to request and track the status of their ILL requests. Additionally, unlike the current process student do not have to input requests using multiple vendor generated ILL forms.
In addition, Technical Services will streamline the current workflow process and work collaboratively with systems and reference to develop training tutorials for faculty and students. The new seamless automated process will enhance and provide significant improvements in patron services and electronic document delivery.

## Slide 6: Migration from Ariel to ILLiad and Odyssey
Phase I - November 8, 2011: Contacted OCLC About ILLiad
Phase II - April 12, 2012: Decided to purchase ILLiad
Phase III - June 5, 2012: ILLiad Setup & Training
Phase IV - September 3, 2012: Implementation (BETA)
Atlas SQL Alias
Manager
ILLiad Client
ILLiad Customization
Manager
ILLiad Staff
Manager

## Slide 7: Phase I - November 8, 2011: Contacted OCLC About ILLiad
Requested a quote from OCLC
Provided the Library ILL statistics for FY 2010 Jan - Dec
Received an introductory tier quote
Library staff attended ILLiad online demonstration on Dec 2011
2010 Lender activity
557 Total
515 articles
42 books
2010 Borrower activity
286 Total
190 Articles
96 Books

## Slide 8: Phase II - April 12, 2012: Decided to purchase ILLiad
Requested an UPDATED quote from OCLC
Received updated quote & ILLiad Implementation Instruction
Ordered ILLiad License, Hosting service & Implementation Service
Attended the May 24, 2012 Resource Sharing webinar, “Leveraging Link Resolvers to Speed Processing” Add-ons for ILLiad

## Slide 9: Phase III - June 5, 2012: ILLiad Setup & Training
Received welcome to ILLiad Implementation packet
Viewed the ILLiad software upgrade for Hosted ILLiad libraries (Recorded June 12, 2012 version) webinar
Provided to OCLC ILLiad configuration information on June 20, 2012
ILLiad hosted server installation completed on July 9, 2012
Completed ILLiad installation wizard and sent SQL file to OCLC on July 25, 2012
    IP Address
    Z39.50

## Slide 10: Phase III - June 5, 2012: ILLiad Setup & Training – Continued
On August 2, 2012 - Installed the ILLiad 8.2 Client on all ILL staff computers

## Slide 11: Phase III - June 5, 2012: ILLiad Setup & Training – Continued
Library staff attended ILLiad online 25-minutes Self-paced online Implementation Kick-Off class on August 3, 2012
Provided to OCLC support a copy of our EZproxy config.txt file on August 3, 2012
Made Marc record information available in OPAC August 23, 2012

## Slide 12: Phase III - June 5, 2012: ILLiad Setup & Training – Continued
Completed ILLiad Online Training
Basic Training (3 hours)
August 30, 2012
Lending Training (3 hours)
August 31, 2012

## Slide 13: Phase IV - September 3, 2012: Implementation (BETA)
Processed Lending requests (BETA) September 3, 2012
Setup ILLiad borrowing remote authentication logon through EZproxy on September 27, 2012

## Slide 14: Phase IV - September 3, 2012: Implementation (BETA) - Continued
Modifying ILLiad user forms September 26, 2012

## Slide 15: Phase IV - September 3, 2012: Implementation (BETA) - Continued
Scheduled ILLiad training
Borrowing Training (3 hours)
October 12, 2012

## Slide 16: Phase IV - September 3, 2012: Implementation (BETA) - Continued
In-House ILLiad Training
Pictured from left to right: Beverly Charlot, Donsha Castro, and Rebecca Batson
Assumptions:
Online Training would result in the staff ready to use the product
The training handouts were adequate
Knowledge Gaps: Time lapse between training and using ILLiad
Action/Results:
Developed Tip-Sheets
Coaching
Improved and clarified processes

## Slide 17: Phase IV - September 3, 2012: Implementation (BETA) - Continued
In-House ILLiad Training
Pictured from left to right: Beverly Charlot, Donsha Castro, and Rebecca Batson
“The tip sheets that were formulated for the ILLiad program made the process easier and understandable for a first time user. They also clarified the workflow and increased my confidence during the learning phase.”
Donsha Castro

## Slide 18: Phase IV - September 3, 2012: Implementation (BETA) - Continued
Marketing
Going Live
Brochures/Flyers
January 2013

## Slide 19: Q & A
Thank You